## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Finalize contract with Terrific Tablets.
Train managers and staff on using the tablets.
Connect marketing team with Terrific Tablets for branding.
Schedule electrician to set up power for tablets.
Plan staffing and support for launch day.
Install tablets at Downtown and North bar areas.
Test online ordering and payment on tablets.
Update and test digital menu on tablets.
Track project costs and compare to budget.
Get staff feedback during soft launch.
Create procedure for locking up tablets after service.
Enable GPS tracking on all tablets.
Add clear payment security messages to tablet screens.
Add payment security points to waitstaff training.
Reviewed Peta’s calls with Seydou, Gilly, and Nia.
Located at least one task per conversation (4 total tasks).
Added these four tasks to the Task Brainstorm tab in the project plan.
Tasks align with training, site-specific considerations, and waitstaff impact for the tablet rollout.
Task | Optimistic Estimate | Most Likely Estimate | Pessimistic Estimate | Confidence Rating (H/M/L) | Notes
Train managers and staff (phased) | 10 days | 14 days | 21 days | M | Training in two phases at multiple locations; confirm schedule with GMs
Wiring for tablet installation | 2 days | 4 days | 6 days | H | Electrician prefers early morning; notify GMs; confirm ISP capacity
POS system integration | 5 days | 10 days | 20 days | L | First time integrating tablets with POS; system upgrade may be required
Upload menu and coupon content | 3 days | 5 days | 7 days | M | Depends on Carter’s final approval and schedule availability

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Restaurant Technology News Article | Restuarant Technology News Article | 2025-07-07 | Tips on tablet security, staff training, and customer messaging.
Upserve Restaurant Tablet Guide | Upserve Restaurant Tablet Guide | 2025-07-07 | Info on secure payments, staff education, and tracking tablets.
Summary Table for your records:
Q# | Answer
1 | Yes
2 | A shipping delay, Broken devices
3 | Carter revamp menu, Carter’s unpredictable schedule
4 | Need POS update, Not running version 3.0
5 | 5 days
6 | 3 days

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
FALSE
|  | Are customers having better dinning experience with the tablets | Percentage of customers reporting satisfaction with tablet ordering on post-visit surveys (target: 85%+). | FALSE
|  | Are the tablets functioning properly during customer use? | Percentage of successful transactions without tablet errors (target: 98%+ success rate per shift). | FALSE
|  | How quickly are the customers learning to navigate tablet quickly? | Average time (in minutes) it takes for a customer to place their first order without staff assistance (goal: under 5 minutes for 80% of users). | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
|  |  | Did you use a tablet during your visit today? | Y/N | Yes | No
|  |  | Was your order correct? | Y/N | Yes | No
|  |  | True or False: The tablet was easy to use. | T/F | TRUE | FALSE
|  |  | On a scale of 1-5, how would you rate the ease of placing an order using the tablet? | Scaled | 1: Needs improvement | 2 | 3 | 4 | 5: Excellent
|  |  | How long did your dinner take tonight? | MC | Under 30 min | 30-45 min | 45-60 min | Over 60 min
|  |  | How satisfied were you with the wait time before being seated? | Scaled | 1: Very dissatisfied | 2 | 3 | 4 | 5: Very satisfied
|  |  | Did you experience any technical issues with the tablet? | Y/N | Yes | No
|  |  | If you experienced issues, please describe them. | Open-ended | Open-ended
|  |  | How likely are you to recommend Sauce & Spoon to a friend after using the tablets? | Scaled | 1: Very unlikely | 2 | 3 | 4 | 5: Very likely
|  |  | Did using the tablet improve your dining experience? | Y/N | Yes | No
|  |  | True or False: The tablet made it easier to view the menu and specials. | T/F | TRUE | FALSE
|  |  | Did you receive your order faster when using the tablet? | Y/N | Yes | No
|  |  | How would you rate the tabletâ€™s appearance and design? | Scaled | 1: Needs improvement | 2 | 3 | 4 | 5: Excellent
|  |  | What did you like most about using the tablet? | Open-ended | Open-ended
|  |  | What improvements would you suggest for the tablet ordering experience? | Open-ended | Open-ended

## Additional Notes
¦ Category ¦ Criteria ¦ Measurement Method ¦ Target/Goal ¦ Owner ¦ Notes ¦
¦------------------¦----------------------------------------------------¦--------------------------------------¦------------------------------------------¦----------------¦-------¦
¦ Customer Satisfaction ¦ Lobby wait time under 10 min ¦ Average wait time from POS data ¦ < 10 min per party ¦ FOH Manager ¦ Use POS timestamps ¦
¦ Customer Satisfaction ¦ Table turn time avg 45 min ¦ Table occupancy reports ¦ 45 min avg per table ¦ FOH Manager ¦ Identify outliers ¦
¦ Customer Satisfaction ¦ Order accuracy 98% ¦ POS vs. delivered order checks ¦ 98%+ accuracy ¦ Shift Lead ¦ Validate daily ¦
¦ Customer Satisfaction ¦ Email capture rate 80% ¦ Email opt-in tracking in system ¦ 80% of tablet users opt-in ¦ Marketing Lead ¦ Review weekly ¦
¦ Customer Satisfaction ¦ Retention increase in tablet areas 5% ¦ Return visit tracking per customer ¦ +5% in tablet areas ¦ Marketing Lead ¦ Compare pre/post launch ¦
¦ Functionality ¦ Tablet battery life min 8 hours per shift ¦ Battery performance logs ¦ 8+ hours without recharge ¦ IT Lead ¦ Replace faulty devices ¦
¦ Functionality ¦ POS integration success ¦ Integration test results ¦ Successful end-to-end transactions ¦ IT Lead ¦ Prior to staff training ¦
¦ Ease-of-use ¦ Staff can complete order in < 2 min ¦ Staff testing/training ¦ 90% staff complete orders < 2 min ¦ Training Lead ¦ Record during training ¦
¦ Ease-of-use ¦ Customer NPS score for tablet ordering ¦ NPS survey on tablet after order ¦ 8.0+ average ¦ Marketing Lead ¦ Weekly report ¦
¦ Design ¦ UI aligns with brand guidelines ¦ Design review checklist ¦ 100% compliance with brand palette ¦ Design Lead ¦ Prior to deployment ¦