## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Customers enjoyed extended time at the tables | Survey comment: 'We liked being able to relax and order at our own pace.' | Maintain flexible ordering flow in final rollout
Customers | Went well | High newsletter signup via tablets | 78% of customers signed up for the newsletter | Continue using tablets for newsletter opt-ins
Customers | Went well | Quick and easy checkout process | Survey: Majority found checkout quick, easy, secure | Maintain current checkout process on tablets
Customers | Needs improvement | 12% of customers experienced technical issues | Survey: 12% reported glitches during ordering | Review and fix technical issues prior to full launch
Customers | Needs improvement | Some customers found navigation confusing | Survey comments indicated confusion with menu navigation | Enhance menu navigation and provide clear prompts
Customers | Needs improvement | Need to improve table turn time | Survey comments mentioned longer table time than expected | Optimize order processing to improve table turn time
Project team | Went well | Guests adapted to using tablets quickly | Retrospective: 'Guests seemed to get the hang of the tablets' | Continue current customer onboarding approach
Project team | Went well | Tickets were easy to track | Retrospective: Tickets came through at a good pace | Maintain current ticket tracking system
Project team | Went well | Staff adapted to tablet use efficiently | Retrospective: Staff quickly learned to use the tablets | Reinforce current training approach for full rollout
Project team | Needs improvement | Table turn time needs improvement | Retrospective: Table turn time remained longer than target | Review workflow and identify efficiencies
Project team | Needs improvement | Orders getting sent back | Retrospective: Some orders had to be corrected | Implement additional checks in ordering system
Project team | Needs improvement | Technical glitches during the test launch | Retrospective: Reports of system freezing during busy periods | Conduct stress testing and resolve performance issues